## README
Panama Infrastructure Delivery Intelligence Platform
Purpose | Independent portfolio project demonstrating project controls, procurement analytics, automation and AI-assisted decision support.
Context | Inspired by publicly available information on international-development infrastructure programmes in Panama.
Important | All operational project, supplier, contract, financial, risk and milestone data in this workbook is simulated.
MVP Stack | Excel → Power BI → Power Automate → Copilot Studio
Programme Value | 70000000
Projects | 12
Primary Users | Programme Manager, Project Manager, Procurement Officer, Project Controls / PMO
Next Step | Connect this workbook to Power BI and build the Executive Overview model before adding automation or the agent.
Core management questions this dataset should answer
1 | Which projects require management attention this week?
2 | Which procurement packages are delaying project delivery?
3 | Which contracts or projects have cost/forecast pressure?
4 | Which suppliers are underperforming?
5 | What milestones are overdue or due within seven days?
6 | What are the highest residual risks and who owns them?

## Projects
Project ID | Project Name | Province | Project Type | Project Manager | Approved Budget | Start Date | End Date | Phase | Physical Progress | RAG Status
PRJ-001 | Panamá Oeste Road Rehabilitation | Panamá Oeste | Road Rehabilitation | María Torres | 8500000 | 2026-01-12 | 2027-03-31 | Construction | 61% | Amber
PRJ-002 | Colón Preventive Maintenance Programme | Colón | Preventive Maintenance | Carlos Méndez | 5200000 | 2026-02-02 | 2026-12-18 | Procurement | 18% | Red
PRJ-003 | Chiriquí Road Asset Rehabilitation | Chiriquí | Road Rehabilitation | Ana Castillo | 7800000 | 2026-01-20 | 2027-05-14 | Construction | 44% | Amber
PRJ-004 | Veraguas Bridge Maintenance Package | Veraguas | Bridge Maintenance | Luis Herrera | 4100000 | 2026-03-02 | 2027-01-29 | Construction | 52% | Green
PRJ-005 | Coclé Rural Connectivity Works | Coclé | Rural Roads | Sofía Ríos | 6100000 | 2026-02-16 | 2027-04-30 | Construction | 39% | Amber
PRJ-006 | Darién Climate-Resilient Access | Darién | Climate Resilience | Jorge Batista | 7200000 | 2026-04-06 | 2027-08-27 | Design | 12% | Amber
PRJ-007 | Panamá Metro Area Road Safety | Panamá | Road Safety | Elena Vega | 4900000 | 2026-03-23 | 2027-02-26 | Construction | 47% | Green
PRJ-008 | Bocas del Toro Drainage & Road Works | Bocas del Toro | Drainage / Roads | Ricardo Peña | 5500000 | 2026-04-20 | 2027-07-30 | Procurement | 15% | Red
PRJ-009 | Herrera Pavement Preservation | Herrera | Pavement Preservation | Paola Díaz | 3800000 | 2026-02-09 | 2026-11-27 | Construction | 68% | Green
PRJ-010 | Los Santos Road Maintenance | Los Santos | Preventive Maintenance | Miguel Soto | 3500000 | 2026-03-09 | 2027-01-15 | Construction | 55% | Green
PRJ-011 | National Road Asset Management Platform | National | Digital Platform | Andrea Gómez | 6200000 | 2026-01-05 | 2027-06-30 | Implementation | 36% | Amber
PRJ-012 | Comarca Ngäbe-Buglé Access Improvements | Ngäbe-Buglé | Rural Roads | Daniel Chan | 7200000 | 2026-05-04 | 2027-10-29 | Design | 9% | Red

## Suppliers
Supplier ID | Supplier Name | Category | Quality Score | Delivery Score | Compliance Score | Overall Score | Performance Status
SUP-001 | Istmo Vial, S.A. | Civil Works | 82 | 76 | 90 | 82.7 | Acceptable
SUP-002 | Constructora Pacífico | Civil Works | 91 | 88 | 94 | 91 | High Performing
SUP-003 | Infraestructura del Caribe | Civil Works | 68 | 62 | 79 | 69.7 | Needs Attention
SUP-004 | Puentes y Caminos Panamá | Bridge Works | 86 | 83 | 92 | 87 | Acceptable
SUP-005 | GeoRoad Engineering | Engineering Services | 93 | 91 | 96 | 93.3 | High Performing
SUP-006 | Servicios Viales del Sur | Maintenance | 77 | 71 | 88 | 78.7 | Acceptable
SUP-007 | Canal Digital Solutions | Technology | 89 | 92 | 95 | 92 | High Performing
SUP-008 | Drenajes Tropicales | Drainage | 72 | 66 | 84 | 74 | Needs Attention

## Procurement
Procurement ID | Project ID | Package | Estimated Value | Planned Award Date | Actual Award Date | Status | Days vs Plan | RAG
PROC-001 | PRJ-001 | Package 1 - Road Rehabilitation | 2122000 | 2026-07-13 |  | Evaluation | 45 | Amber
PROC-002 | PRJ-001 | Package 2 - Road Rehabilitation | 2647000 | 2026-03-06 |  | Planning | 174 | Red
PROC-003 | PRJ-002 | Package 1 - Preventive Maintenance | 692000 | 2026-06-02 |  | Evaluation | 86 | Red
PROC-004 | PRJ-002 | Package 2 - Preventive Maintenance | 887000 | 2026-04-28 |  | Solicitation | 121 | Red
PROC-005 | PRJ-003 | Package 1 - Road Rehabilitation | 1323000 | 2026-03-17 | 2026-03-16 | Award | -1 | Green
PROC-006 | PRJ-003 | Package 2 - Road Rehabilitation | 2074000 | 2026-06-27 | 2026-06-27 | Contracted | 0 | Green
PROC-007 | PRJ-004 | Package 1 - Bridge Maintenance | 993000 | 2026-05-03 | 2026-05-01 | Award | -2 | Green
PROC-008 | PRJ-004 | Package 2 - Bridge Maintenance | 1031000 | 2026-04-14 |  | Planning | 135 | Red
PROC-009 | PRJ-005 | Package 1 - Rural Roads | 1763000 | 2026-06-28 | 2026-07-09 | Award | 11 | Green
PROC-010 | PRJ-005 | Package 2 - Rural Roads | 900000 | 2026-04-11 | 2026-04-20 | Contracted | 9 | Green
PROC-011 | PRJ-006 | Package 1 - Climate Resilience | 1878000 | 2026-05-29 |  | Solicitation | 90 | Red
PROC-012 | PRJ-006 | Package 2 - Climate Resilience | 1006000 | 2026-04-25 |  | Evaluation | 124 | Red
PROC-013 | PRJ-007 | Package 1 - Road Safety | 1481000 | 2026-01-24 | 2026-01-24 | Contracted | 0 | Green
PROC-014 | PRJ-007 | Package 2 - Road Safety | 755000 | 2026-07-15 |  | Solicitation | 43 | Amber
PROC-015 | PRJ-008 | Package 1 - Drainage / Roads | 952000 | 2026-01-28 |  | Solicitation | 211 | Red
PROC-016 | PRJ-008 | Package 2 - Drainage / Roads | 1733000 | 2026-06-30 |  | Planning | 58 | Red
PROC-017 | PRJ-009 | Package 1 - Pavement Preservation | 800000 | 2026-02-22 |  | Evaluation | 186 | Red
PROC-018 | PRJ-009 | Package 2 - Pavement Preservation | 1132000 | 2026-06-11 | 2026-06-10 | Award | -1 | Green
PROC-019 | PRJ-010 | Package 1 - Preventive Maintenance | 636000 | 2026-05-07 | 2026-05-24 | Award | 17 | Green
PROC-020 | PRJ-010 | Package 2 - Preventive Maintenance | 429000 | 2026-02-24 |  | Evaluation | 184 | Red
PROC-021 | PRJ-011 | Package 1 - Digital Platform | 964000 | 2026-04-16 | 2026-04-14 | Contracted | -2 | Green
PROC-022 | PRJ-011 | Package 2 - Digital Platform | 1386000 | 2026-02-27 |  | Solicitation | 181 | Red
PROC-023 | PRJ-012 | Package 1 - Rural Roads | 1965000 | 2026-05-20 | 2026-05-20 | Contracted | 0 | Green
PROC-024 | PRJ-012 | Package 2 - Rural Roads | 1346000 | 2026-01-29 | 2026-02-14 | Award | 16 | Green

## Contracts
Contract ID | Project ID | Supplier ID | Supplier Name | Contract Value | Committed | Actual Spend | Forecast at Completion | Forecast Variance | Contract Start | Contract End | Status
CON-001 | PRJ-001 | SUP-001 | Istmo Vial, S.A. | 5609000 | 3847000 | 3110000 | 6130000 | 521000 | 2026-02-10 | 2027-03-31 | At Risk
CON-002 | PRJ-002 | SUP-002 | Constructora Pacífico | 2481000 | 1874000 | 1083000 | 2396000 | -85000 | 2026-02-19 | 2026-12-18 | On Track
CON-003 | PRJ-003 | SUP-003 | Infraestructura del Caribe | 3568000 | 2420000 | 2052000 | 3729000 | 161000 | 2026-02-28 | 2027-05-14 | On Track
CON-004 | PRJ-004 | SUP-004 | Puentes y Caminos Panamá | 2579000 | 2543000 | 1283000 | 2760000 | 181000 | 2026-03-09 | 2027-01-29 | On Track
CON-005 | PRJ-005 | SUP-005 | GeoRoad Engineering | 3496000 | 2221000 | 1699000 | 3944000 | 448000 | 2026-03-18 | 2027-04-30 | At Risk
CON-006 | PRJ-006 | SUP-006 | Servicios Viales del Sur | 3316000 | 2455000 | 1929000 | 3654000 | 338000 | 2026-03-27 | 2027-08-27 | At Risk
CON-007 | PRJ-007 | SUP-007 | Canal Digital Solutions | 2497000 | 2451000 | 1491000 | 2355000 | -142000 | 2026-04-05 | 2027-02-26 | On Track
CON-008 | PRJ-008 | SUP-008 | Drenajes Tropicales | 2820000 | 2034000 | 1822000 | 3114000 | 294000 | 2026-04-14 | 2027-07-30 | At Risk
CON-009 | PRJ-009 | SUP-001 | Istmo Vial, S.A. | 2752000 | 2537000 | 1213000 | 3183000 | 431000 | 2026-04-23 | 2026-11-27 | At Risk
CON-010 | PRJ-010 | SUP-002 | Constructora Pacífico | 1624000 | 939000 | 456000 | 1610000 | -14000 | 2026-05-02 | 2027-01-15 | On Track
CON-011 | PRJ-011 | SUP-003 | Infraestructura del Caribe | 4734000 | 3892000 | 2588000 | 4692000 | -42000 | 2026-05-11 | 2027-06-30 | On Track
CON-012 | PRJ-012 | SUP-004 | Puentes y Caminos Panamá | 4116000 | 2783000 | 2078000 | 4015000 | -101000 | 2026-05-20 | 2027-10-29 | On Track

## Milestones
Milestone ID | Project ID | Milestone | Planned Date | Actual Date | Status | Days Variance / Overdue
MIL-001 | PRJ-001 | Design Complete | 2026-04-12 |  | Overdue | 137
MIL-002 | PRJ-001 | Procurement Award | 2026-06-11 | 2026-06-09 | Completed | -2
MIL-003 | PRJ-001 | 50% Physical Completion | 2026-09-19 |  | Overdue | -23
MIL-004 | PRJ-001 | Substantial Completion | 2027-02-06 |  | On Track | -163
MIL-005 | PRJ-002 | Design Complete | 2026-05-03 | 2026-05-16 | Completed | 13
MIL-006 | PRJ-002 | Procurement Award | 2026-07-02 | 2026-07-10 | Completed | 8
MIL-007 | PRJ-002 | 50% Physical Completion | 2026-10-10 |  | On Track | -44
MIL-008 | PRJ-002 | Substantial Completion | 2027-02-27 |  | On Track | -184
MIL-009 | PRJ-003 | Design Complete | 2026-04-20 | 2026-05-04 | Completed | 14
MIL-010 | PRJ-003 | Procurement Award | 2026-06-19 |  | Overdue | 69
MIL-011 | PRJ-003 | 50% Physical Completion | 2026-09-27 |  | Overdue | -31
MIL-012 | PRJ-003 | Substantial Completion | 2027-02-14 |  | On Track | -171
MIL-013 | PRJ-004 | Design Complete | 2026-05-31 |  | Overdue | 88
MIL-014 | PRJ-004 | Procurement Award | 2026-07-30 |  | Overdue | 28
MIL-015 | PRJ-004 | 50% Physical Completion | 2026-11-07 |  | On Track | -72
MIL-016 | PRJ-004 | Substantial Completion | 2027-03-27 |  | On Track | -212
MIL-017 | PRJ-005 | Design Complete | 2026-05-17 | 2026-05-16 | Completed | -1
MIL-018 | PRJ-005 | Procurement Award | 2026-07-16 | 2026-07-23 | Completed | 7
MIL-019 | PRJ-005 | 50% Physical Completion | 2026-10-24 |  | On Track | -58
MIL-020 | PRJ-005 | Substantial Completion | 2027-03-13 |  | On Track | -198
MIL-021 | PRJ-006 | Design Complete | 2026-07-05 |  | Overdue | 53
MIL-022 | PRJ-006 | Procurement Award | 2026-09-03 |  | On Track | -7
MIL-023 | PRJ-006 | 50% Physical Completion | 2026-12-12 |  | On Track | -107
MIL-024 | PRJ-006 | Substantial Completion | 2027-05-01 |  | On Track | -247
MIL-025 | PRJ-007 | Design Complete | 2026-06-21 |  | Overdue | 67
MIL-026 | PRJ-007 | Procurement Award | 2026-08-20 |  | On Track | 7
MIL-027 | PRJ-007 | 50% Physical Completion | 2026-11-28 |  | On Track | -93
MIL-028 | PRJ-007 | Substantial Completion | 2027-04-17 |  | On Track | -233
MIL-029 | PRJ-008 | Design Complete | 2026-07-19 | 2026-07-18 | Completed | -1
MIL-030 | PRJ-008 | Procurement Award | 2026-09-17 |  | Overdue | -21
MIL-031 | PRJ-008 | 50% Physical Completion | 2026-12-26 |  | On Track | -121
MIL-032 | PRJ-008 | Substantial Completion | 2027-05-15 |  | On Track | -261
MIL-033 | PRJ-009 | Design Complete | 2026-05-10 | 2026-05-11 | Completed | 1
MIL-034 | PRJ-009 | Procurement Award | 2026-07-09 | 2026-07-05 | Completed | -4
MIL-035 | PRJ-009 | 50% Physical Completion | 2026-10-17 |  | On Track | -51
MIL-036 | PRJ-009 | Substantial Completion | 2027-03-06 |  | On Track | -191
MIL-037 | PRJ-010 | Design Complete | 2026-06-07 | 2026-06-11 | Completed | 4
MIL-038 | PRJ-010 | Procurement Award | 2026-08-06 |  | Due Soon | 21
MIL-039 | PRJ-010 | 50% Physical Completion | 2026-11-14 |  | On Track | -79
MIL-040 | PRJ-010 | Substantial Completion | 2027-04-03 |  | On Track | -219
MIL-041 | PRJ-011 | Design Complete | 2026-04-05 | 2026-04-03 | Completed | -2
MIL-042 | PRJ-011 | Procurement Award | 2026-06-04 | 2026-06-20 | Completed | 16
MIL-043 | PRJ-011 | 50% Physical Completion | 2026-09-12 |  | On Track | -16
MIL-044 | PRJ-011 | Substantial Completion | 2027-01-30 |  | On Track | -156
MIL-045 | PRJ-012 | Design Complete | 2026-08-02 |  | On Track | 25
MIL-046 | PRJ-012 | Procurement Award | 2026-10-01 |  | On Track | -35
MIL-047 | PRJ-012 | 50% Physical Completion | 2027-01-09 |  | On Track | -135
MIL-048 | PRJ-012 | Substantial Completion | 2027-05-29 |  | On Track | -275

## Risks
Risk ID | Project ID | Risk Category | Probability (1-5) | Impact (1-5) | Inherent Score | Residual Score | Residual Level | Owner | Status
RSK-001 | PRJ-001 | Schedule | 2 | 3 | 6 | 2 | Low | María Torres | Monitoring
RSK-002 | PRJ-001 | Procurement | 5 | 2 | 10 | 8 | Medium | María Torres | Monitoring
RSK-003 | PRJ-002 | Environmental | 3 | 2 | 6 | 1 | Low | Carlos Méndez | Monitoring
RSK-004 | PRJ-002 | Stakeholder | 5 | 4 | 20 | 17 | Critical | Carlos Méndez | Monitoring
RSK-005 | PRJ-003 | Cost | 3 | 5 | 15 | 9 | Medium | Ana Castillo | Open
RSK-006 | PRJ-003 | Environmental | 2 | 4 | 8 | 6 | Medium | Ana Castillo | Open
RSK-007 | PRJ-004 | Procurement | 4 | 5 | 20 | 16 | Critical | Luis Herrera | Open
RSK-008 | PRJ-004 | Technical | 3 | 2 | 6 | 1 | Low | Luis Herrera | Monitoring
RSK-009 | PRJ-005 | Technical | 2 | 3 | 6 | 5 | Medium | Sofía Ríos | Monitoring
RSK-010 | PRJ-005 | Schedule | 5 | 2 | 10 | 6 | Medium | Sofía Ríos | Monitoring
RSK-011 | PRJ-006 | Environmental | 3 | 4 | 12 | 6 | Medium | Jorge Batista | Mitigating
RSK-012 | PRJ-006 | Environmental | 4 | 5 | 20 | 17 | Critical | Jorge Batista | Open
RSK-013 | PRJ-007 | Stakeholder | 5 | 4 | 20 | 17 | Critical | Elena Vega | Mitigating
RSK-014 | PRJ-007 | Environmental | 4 | 5 | 20 | 18 | Critical | Elena Vega | Monitoring
RSK-015 | PRJ-008 | Stakeholder | 3 | 3 | 9 | 7 | Medium | Ricardo Peña | Mitigating
RSK-016 | PRJ-008 | Procurement | 2 | 4 | 8 | 2 | Low | Ricardo Peña | Monitoring
RSK-017 | PRJ-009 | Procurement | 3 | 5 | 15 | 11 | High | Paola Díaz | Mitigating
RSK-018 | PRJ-009 | Schedule | 4 | 2 | 8 | 6 | Medium | Paola Díaz | Monitoring
RSK-019 | PRJ-010 | Supplier | 5 | 2 | 10 | 9 | Medium | Miguel Soto | Open
RSK-020 | PRJ-010 | Cost | 4 | 2 | 8 | 7 | Medium | Miguel Soto | Open
RSK-021 | PRJ-011 | Procurement | 4 | 5 | 20 | 15 | High | Andrea Gómez | Mitigating
RSK-022 | PRJ-011 | Schedule | 2 | 3 | 6 | 1 | Low | Andrea Gómez | Mitigating
RSK-023 | PRJ-012 | Technical | 2 | 2 | 4 | 2 | Low | Daniel Chan | Monitoring
RSK-024 | PRJ-012 | Stakeholder | 4 | 3 | 12 | 11 | High | Daniel Chan | Open

## Financials
Project ID | Approved Budget | Committed | Actual Spend | Forecast at Completion | Forecast Variance | Variance %
PRJ-001 | 8500000 | 5940000 | 2727000 | 8805000 | 305000 | 3.588%
PRJ-002 | 5200000 | 3027000 | 2182000 | 5286000 | 86000 | 1.654%
PRJ-003 | 7800000 | 3042000 | 1394000 | 7727000 | -73000 | -0.9359%
PRJ-004 | 4100000 | 1619000 | 835000 | 4305000 | 205000 | 5%
PRJ-005 | 6100000 | 4673000 | 2408000 | 6349000 | 249000 | 4.082%
PRJ-006 | 7200000 | 4166000 | 2870000 | 8010000 | 810000 | 11.25%
PRJ-007 | 4900000 | 2573000 | 1716000 | 5040000 | 140000 | 2.857%
PRJ-008 | 5500000 | 2316000 | 1441000 | 6129000 | 629000 | 11.44%
PRJ-009 | 3800000 | 2648000 | 1388000 | 3800000 | 0 | 0%
PRJ-010 | 3500000 | 1542000 | 928000 | 3580000 | 80000 | 2.286%
PRJ-011 | 6200000 | 2565000 | 1563000 | 6927000 | 727000 | 11.73%
PRJ-012 | 7200000 | 3847000 | 2641000 | 8034000 | 834000 | 11.58%

## Data Dictionary
Table | Purpose | Key Field | Used for
Projects | Master list of infrastructure workstreams | Project ID | Programme overview, scope, progress, RAG
Procurement | Procurement packages and award timing | Procurement ID | Pipeline, delays, procurement lead-time alerts
Contracts | Supplier contracts and financial outlook | Contract ID | Contract value, forecast pressure, supplier linkage
Suppliers | Supplier performance scorecard | Supplier ID | Quality, delivery, compliance and agent exception detection
Milestones | Planned and actual delivery milestones | Milestone ID | Schedule performance and due/overdue alerts
Risks | Programme and project risk register | Risk ID | Risk prioritization, owners and mitigation status
Financials | Project-level budget/forecast position | Project ID | Budget vs actual/forecast and financial escalation